## APP Non CSE 2023
Department of Education
Region III
DIVISION OF CITY SCHOOLS
Angeles City
Jesus Street, Pulungbulu, Angeles City
Tel. No. (045) 322-4106; 322-4101; 322-4702 / Fax Nos. (045) 887-6099
DepEd Angeles City Indicative FY 2023 Annual Procurement Plan Non CSE | [12 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Code (PAP) | Procurement Program/ Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (Brief description of Program/Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Ads/ Post of IB/REI | Sub/ Open of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
A. FURNITURES & EQUIPMENTS
| Office Equipments | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| ICT Equipment | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| Furniture & Fixture | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| Office Equipments | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
| ICT Equipment | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
| Furniture & Fixture | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
B. REPAIR OF SCHOOL BUILDINGS
C. PROFESSIONAL SERVICES
| Janitorial Manpower Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 228000
| Security Manpower Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A |  |  | 648000
| Job Order | OSDS, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1011000
D. SUPPLIES AND MATERIALS
| Common use supplies and materials available at the Procurement Office | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 400000 |  | Procurement Service
| Supplies and Materials not available at the Procurement Service | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 420000 |  | Outside Suppliers
| Printing materials (RISO ink and Riso Master) | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 50000 |  | UBIX COR./ HP
| Photocopier Ink & Parts | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 50000 |  | UBIX CORP.
| Tires / Automotive batt. | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 30000 |  | Outside Suppliers
E. UTILITIES
| Water Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 420000 |  | Angeles City Water District
| Electricity Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 2280000 |  | Angeles Electric Corporation
F. COMMUNICATION
| Telephone and Internet Connection | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1075500 |  | Datelcom, Globe, Converge
G. REPAIR AND MAINTENANCE
| Motor Vehicle | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 300000 |  | Preventive Maintenance for Motor Vehicles
| Air Conditioners | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 100000 |  | Cleaning and Preventive Maintenance of Airconditioners
H. TRAININGS/SEMINARS
| Organizational Program Development for Non-Teaching Personnel | SGOD | NP - Small Value | N/A | N/A | N/A | N/A | SARO |  | 281000 |  | Various Trainings for Non- Teaching Personnel
| Trainings for Teaching, Teaching Related and Non Teaching in the Division | OSDS CID SGOD | NP- Small Value | N/A | N/A | N/A | N/A | Division -INSET Funds |  | 75000 |  | Various trainings in the Division
[8 empty] | Total: |  | 7368500 | 0
DEFINITION | [9 empty] | Remarks
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions. | [8 empty] | Programs and projects should be alligned with budget documents, and especially those posted at the PhilGeps.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (pre-procurement conference; advertising/posting; pre-bid conference; eligibility screening; submission and receipt of bids; bid evalutaion; post qualification; award of contract; contract preparation), delivery/completion and acceptance/turnover.
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund | [8 empty] | Breakdwon into MOOE and
7. Estimated Budget - Agency approved estimate of project/program costs | [8 empty] | any remark that will help
8. Remarks - brief description of program or project | [8 empty] | GPPB track programs and
projects.
| Prepared by: |  |  | Recommending approval: |  |  |  |  | Approved:
| MARIA CRISTINA S. SARMIENTO |  |  | FERNANDINA P. OTCHENGCO PhD, CESE |  |  |  |  | MA. IRELYN P. TAMAYO PhD, CESO VI
| BAC Secretariat |  |  | Asst. Schools Division Superintendent |  |  |  |  | Schools Division Superintendent