## pmr 2021
|  | ANNEX A | ANNEX B
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| CY2021 BEFF Repair of Classrooms School | Angeles City National Trade School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 3116479.76 | 0 | 3116479.76 | 3111464.79 | 0 | 3111464.79 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Francisco G. Nepomuceno Memorial High School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2923827.98 | 0 | 2923827.98 | 2916984.81 | 0 | 2916984.81 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Rafael L. Lazatin MHS | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2515459.64 | 0 | 2515459.64 | 2509960.73 | 0 | 2509960.73 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Angeles City National High School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 7096381.72 | 0 | 7096381.72 | 7086139.77 | 0 | 7086139.77 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Cutud ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344133.09 | 0 | 1344133.09 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Northville 15 IS | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Epza Rest ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1800000 | 0 | 1800000 | 1794988.33 | 0 | 1794988.33 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Pulung Bulu ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Sto. Domingo IS | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2700000 | 0 | 2700000 | 2689371.37 | 0 | 2689371.37 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Apung Guidang ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 500000 | 0 | 500000 | 494888.88 | 0 | 494888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Angeles ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 3600000 | 0 | 3600000 | 3593489.6 | 0 | 3593489.6 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Sta. Teresita ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 4950000 | 0 | 4950000 | 4938888.88 | 0 | 4938888.88 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Pampang ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2250000 | 0 | 2250000 | 2245474.37 | 0 | 2245474.37 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Sapalibutad ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344568.33 | 0 | 1344568.33 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Pulung Cacutud ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Salapungan ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1345777.5 | 0 | 1345777.5 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | San Ignacio ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1800000 | 0 | 1800000 | 1794767.82 | 0 | 1794767.82 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Belen Homesite ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344960.94 | 0 | 1344960.94 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Air Force ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344973.74 | 0 | 1344973.74 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Gueco Balibago ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2250000 | 0 | 2250000 | 2244540.91 | 0 | 2244540.91 |  | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
GOODS
1 | PRINTING SERVICES FOR THE PROVISION OF EPP, TLE & SENIOR LEARNING RECOURCES FOR QUARTERS 3 & 4 OF SY 2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 17, 2021 | March 24, 2021 | March 26, 2021 | April 12, 2021 | April 12, 2021 | April 12, 2021 | April 14, 2021 | April 15, 2021 | April 29, 2021 | May 3, 2021 | May 17 2021 | May 17 2021 |  | 6149329 |  |  | 4796476.62 |  | 4796476.62 | COA and ACPST-CCI | March 19, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021
2 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR KINDER TO GRADE 3 LEARNERS FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 18, 2021 | March 24, 2021 | March 30, 2021 | April 13, 2021 | April 13, 2021 | April 13, 2021 | April 14, 2021 | April 15, 2021 | April 26, 2021 | May 3, 2021 | May 17 2021 | May 17 2021 |  | 6051427.26 |  |  | 3624788.6 |  | 3624788.6 | COA and ACPST-CCI | March 23, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021
3 | PROCUREMENT OF PRINTERS AND INK FOR THE PROVISION OF LEARNING RESOURCES FOR ARTS, PHYSICAL EDUCATION, ARALING PANLIPUNAN, EDUKASYON PAGPAPAPAKATAO, AND MUSIC FOR QUARTER 3 SY2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 19, 2021 | March 24, 2021 | March 31, 2021 | April 15, 2021 | April 15, 2021 | April 15, 2021 | April 16, 2021 | April 19, 2021 | April 26, 2021 | April 28, 2021 | May 28, 2021 | May 28, 2021 |  | 1947250 |  |  | 1928722 |  | 1928722 | COA and ACPST-CCI | March 23, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021
5 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 -BATCH 2 | DepEd Angeles City |  | Competitive Bidding | April 23, 2021 | April 30, 2021 | May 11, 2021 | May 18, 2021 | May 18, 2021 | May 18, 2021 | May 19, 2021 | May 21, 2021 | May 24, 2021 | May 26, 2021 | June 9, 2021 | June 9, 2021 |  | 2788959.07 |  |  | 2765679 |  | 2765679 | COA and ACPST-CCI | May 4, 2021 | May 11, 2021 | May 11, 2021 | May 11, 2021 | May 11, 2021 | June 2, 2021
7 | PROCUREMENT OF LONG BONDPAPERS FOR THE PROVISION OF LEARNING RESOURCES FOR QUARTER 3 SY2020-2021 - BATCH 2 | DepEd Angeles City |  | Competitive Bidding | N/A | June 23, 2021 | July 1, 2021 | July 13, 2021 | July 13, 2021 | July 13, 2021 | July 14, 2021 | July 16, 2021 | July 26, 2021 | July 27, 2021 | August 14, 2021 | August 14, 2021 |  | 1009060 |  | 6149329 | 1009018 |  | 1009018 | COA and ACPST-CCI | June 16, 2021 | June 16, 2021 | June 16, 2021 | June 16, 2021 | June 16, 2021 | August 7, 2021
8 | PROCUREMENT OF A4 SIZE BOND PAPERS FOR THE IMPLEMENTATION OF BE-LCP PROVISION OF LEARNING RESOURCES AS PER JOINT MEMORANDUM DM-OUCI-2021-107 DATED APRIL 12, 2021 | DepEd Angeles City |  | Competitive Bidding | N/A | June 3, 2021 | June 10, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 9, 2021 | July 12, 2021 | July 27, 2021 | July 27, 2021 |  | 1002765 |  | 6051427.26 | 732, 294.00 |  | 732, 294.00 | COA and ACPST-CCI | June 3, 2021 | June 3, 2021 | June 3, 2021 | June 3, 2021 | June 3, 2021 | July 20, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 |  | 1412287 |  | 1947250 | 1388742 |  | 1388742 | COA and ACPST-CCI | August 11, 2021 | August 24, 2021 | August 24, 2021 | August 24, 2021 | August 24, 2021 | September 28, 2021
10 | Procurement of Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System | DepEd Angeles City |  | Competitive Bidding | August 12, 2021 | August 16, 2021 | August 23, 2021 | September 7, 2021 | September 7, 2021 | September 7, 2021 | September 9, 2021 | September 13, 2021 | September 24, 2021 | September 27, 2021 | November 27, 2021 | November 27, 2021 |  | 1000000 |  | 962907 | 940000 |  | 940000 | COA and ACPST-CCI | August 3, 2021 | August 16, 2021 | August 16, 2021 | August 16, 2021 | August 16, 2021 | November 20, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 |  | 6911464 |  | 2788959.07 | P 4,892,572.00 |  | P 4,892,572.00 | COA and ACPST-CCI | August 2, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | September 28, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 |  | 11133714 |  | 1009060 | 7, 562, 043.00 |  | 7, 562, 043.00 | COA and ACPST-CCI | August 2, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | September 28, 2021
| Procurement of Long Bond Papers for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (18,798 reams) | DepEd Angeles City |  | Competitive Bidding | November 16, 2021 | November 17, 2021 | November. 25, 2021 | November. 29, 2021 | November. 29, 2021 | November 29, 2021 | December 1, 2021 | December 3, 2021 | December 10, 2021 | December 13, 2021 | December 28, 2021 | December 28, 2021 |  | 3571671 |  | 1002765 | 2488859.2 |  | 2488859.2 | COA and ACPST-CCI | November 18, 2021 | November 18, 2021 | November 18, 2021 | November 18, 2021 | November 18, 2021 | December 21, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (8075 pcs) | DepEd Angeles City |  | Competitive Bidding | September 14, 2021 | September 20, 2021 | September 28, 2021 | November 16, 2021 | November 16, 2021 | November 16, 2021 | November 17, 2021 | November 17, 2021 | November 19, 2021 | November 23, 2021 | December 15, 2021 | December 15, 2021 |  | 2018892 |  | 1412287 | P 1, 287,962.50 |  | P 1, 287,962.50 | COA and ACPST-CCI | September 21, 2021 | November 10, 2021 | November 10, 2021 | November 10, 2021 | November 10, 2021 | December7, 2021
| School Based Feeding Program | DepEd Angeles City |  | (2 Failed Bidding) Negotiated Bidding | October 26, 2021 | November 4, 2021 | November 9, 2021 | November 12, 2021 | November 12, 2021 | November 12, 2021 | November 15, 2021 | November 18, 2021 | November 22, 2021 | November 25, 2021 | January 31, 2021 | January 31, 2021 |  | 12, 875,760.00 |  | 1000000 | 12869751.31 |  | 12869751.31 | COA and ACPST-CCI | October 28, 2021 | October 28, 2021 | October 28, 2021 | October 28, 2021 | October 28, 2021
| Purchase of SPED Equipment and Materials for SPED Inclusive Learning Resource Center (ILRC) | DepEd Angeles City |  | Competitive Bidding | October 20, 2021 | October 25, 2021 | November 3, 2021 | November 16, 2021 | November 16, 2021 | November 16, 2021 | November 17, 2021 | November 19, 2021 | November 22, 2021 | November 23, 2021 | December 23, 2021 | December 23, 2021 |  | 2000000 |  | 6911464 | 1795000 |  | 1795000 | COA and ACPST-CCI | October 28, 2021 | November 9, 2021 | November 9, 2021 | November 9, 2021 | December 15, 2021
| Procurement of Technical-Vocational-Livelihood (TVL) Learning Tools and Equipment | DepEd Angeles City |  | Competitive Bidding | November 22, 2021 | November 24, 2021 | December 2, 2021 | December 14, 2021 | December 14, 2021 | December 14, 2021 | December 15, 2021 | December 17, 2021 | January 3, 2022 | January 10, 2022 | February 15, 2022 | February 15, 2022 |  | 2160791 |  | 11133714 | 2,017, 285.00 |  | 2,017, 285.00 | COA and ACPST-CCI | November 26 2021 | December 7, 2021 | December 7, 2021 | December 7, 2021 | December 7, 2021
12, 875,760.00
2000000
2160791
|  |  |  | Prepared: | [10 empty] | Reviewed: | [5 empty] | 0
|  |  | Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  |  | MARIA CRISTINA S. SARMIENTO | MARIA CRISTINA S, SARMIENTO | [7 empty] | FERNANDINA P. OTCHENGCO, PhD CESE |  |  | FERNANDINA P. OTCHENGCO | [7 empty] | MA. IRELYN P. TAMAYO, PhD CESE
|  |  | BAC Secretariat | BAC Secretariat | [7 empty] | BAC Chairperson |  |  | BAC Chair | [7 empty] | Head of the Procuring Entity

## Procurement Status 2021
| SARO NO. | DATE OF SARO | TITLE | ALLOTMENT |  | MODE OF PROCUREMENT | PRE-PROCUREMENT | PRE-BID CONFERENCE | BID OPENING | CONTRACTOR | BID AMOUNT | RTA | NOA | CONTRACT | NTP | DELIVERY | SAVINGS | UTILIZATION | DISBURSEMENT | BALANCE
1 | DEPED-ROIII-2021-03-055 | MARCH 1, 2021 | PRINTING SERVICES FOR THE PROVISION OF EPP, TLE & SENIOR LEARNING RECOURCES FOR QUARTERS 3 & 4 OF SY 2020-2021 | 6149329 |  | COMPETITIVE BIDDING | MARCH 17, 2021 | MARCH 26, 2021 | APRIL 12, 2021 | CRISMAN PRINTING SERVICES | 4796476.62 | [5 empty] | 1352852.38 | 4796476.62 | 0 | 1352852.38 | savings procured
2 | DEPED-ROIII-2021-02-026 | FEBRUARY 10, 2021 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR KINDER TO GRADE 3 LEARNERS FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 | 6051427.26 |  | COMPETITIVE BIDDING | MARCH 18, 2021 | MARCH 30, 2021 | APRIL 13, 2021 | FORGEMS MARKETING COMPANY INC. | 3624788.6 | [5 empty] | 2426638.66 | 3624788.6 | 0 | 2426638.66
3 | DEPED-ROIII-2021-03-088 | MARCH 8, 2021 | PROCUREMENT OF PRINTERS AND INK FOR THE PROVISION OF LEARNING RESOURCES FOR ARTS, PHYSICAL EDUCATION, ARALING PANLIPUNAN, EDUKASYON PAGPAPAPAKATAO, AND MUSIC FOR QUARTER 3 SY2020-2021 | 1947250 |  | COMPETITIVE BIDDING | MARCH 19, 2021 | MARCH 31, 2021 | APRIL 15, 2021 | GAKKEN PHILIPPINES INC. | 1928722 | [5 empty] | -1928722 | 1928722 | 0 | 18528
5 | DEPED-ROIII-2021-03-146 | MARCH 23, 2021 | PROVISION OF LEARNING RESOURCES FOR GRADE 4 - GRADE 10 3RD QUARTER REQUIREMENTS OF SY 2020-2021 | 962907 |  | SMALL VALUE PROCUREMENT/NEGOTIATED PROCUREMENT | N/A | N/A | APRIL 27, 2021 | MGD PRINTING | 770325.6 |  | FOR REPEAT ORDER |  |  |  | 192581.4 | 0 | 0 | 192581.4
6 | OSEC-3-20-2816 | DECEMBER 22, 2020 | RELEASE OF ADDITIONAL MOOE FOR SCHOOL DIVISION OFFICEof (SDO) 1,000,000 |  |  | 501,000.00 (RFQ for anti covid equipment) | N/A | N/A
7 | DEPED-ROIII-2021-03-055 | MARCH 1, 2021 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 -BATCH 2 |  | 2788959.07 | COMPETITIVE BIDDING | APRIL 23, 2021 | MAY 11, 2021 | MAY 24, 2021 | NED ARNNIE ENTERPRISES | 2765679 |  | FOR REPEAT ORDER |  |  |  | -2765679
9 | DEPED-ROIII-2021-02-026 | FEBRUARY 10, 2021 | PROCUREMENT OF LONG BONDPAPERS FOR THE PROVISION OF LEARNING RESOURCES FOR QUARTER 3 SY2020-2021 - BATCH 2 |  | 1009060 | COMPETITIVE BIDDING | N/A | JULY 1, 2021 | JULY 6, 2021 | NED ARNNIE ENTERPRISES | 1009018 |  | DELIVERED
10 | DEPED-ROIII-2021-05-298 | MAY 4, 2021 | PROCUREMENT OF A4 SIZE BOND PAPERS FOR THE IMPLEMENTATION OF BE-LCP PROVISION OF LEARNING RESOURCES AS PER JOINT MEMORANDUM DM-OUCI-2021-107 DATED APRIL 12, 2021 | 1002765 |  | COMPETITIVE BIDDING | N/A | JUNE 3, 2021 | JUNE 16, 2021 | TRIPLEX ENTERPRISES | 732, 294.00 |  | DELIVERED |  |  |  | 270471
11 | DEPED-ROIII-2021-05-318 | MAY 4, 2021 | PROCUREMENT OF LONG BOND PAPERS FOR THE IMPLEMENTATION OF BE-LCP PROVISION OF LEARNING RESOURCES AS PER JOINT MEMORANDUM DM-OUCI-2021-098 DATED APRIL 16, 2021 | 1412287 |  | COMPETITIVE BIDDING | N/A | JUNE 3, 2021 | JUNE 16, 2021 | NED ARNNIE ENTERPRISES | 1388742 |  | DELIVERED |  |  |  | 23545
12 |  |  | Procurement of Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System | 1000000 |  | COMPETITIVE BIDDING |  |  | September 7, 2021 | HYPERNET-INTERNET & BUSINESS SOLUTIONS, INC. | 940000 |  | DELIVERED
|  |  | Procurement of Ubiquiti Switches Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System |  | 60000 | CONTIGUOUS PROCUREMENT | N/A | N/A | N/A | HYPERNET-INTERNET & BUSINESS SOLUTIONS, INC. | 60000 |  | DELIVERED
13 | DEPED-ROIII-2021-07-1428 | JULY 2, 2021 | Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | 6911464 |  | COMPETITIVE BIDDING | August 6, 2021 | August 18, 2021 | August 31, 2021 | Roman Instructional Media Resources, Inc | P 4,892,572.00 |  | DELIVERED
14 | DEPED-ROIII-2021-08-1492 | AUGUST 16, 2021 | Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | 11133714 |  | COMPETITIVE BIDDING | August 27, 2021 | September 9, 2021 | September 21, 2021 | FAYE AND SAM GENERAL MERCHANDISE | 7, 562, 043.00 |  | DELIVERED
16 |  | AUGUST 16, 2021 | Procurement of Long Bond Papers for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (18,798 reams) |  | 3571671 | COMPETITIVE BIDDING | November 16, 2021 | November 25, 2021 | November. 29, 2021 | NAPPCO | 2488859.2
16 | DEPED-ROIII-2021-07-1428 | JULY 2, 2021 | Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (8075 pcs) | 2018892 |  | COMPETITIVE BIDDING | September 14, 2021 | September 28, 2021 | October 12, 2021 | FAYE AND SAM GENERAL MERCHANDISE | P 1, 287,962.50
|  |  | School Based Feeding Program |  |  |  | Failed Bidding |  | September 28, 2021
Failed Bidding
Negotiated Bidding
17 | SUB-ARO Order No. DEPED-ROIII-2021-09-2030 | AUGUST 27, 2021 | Purchase of SPED Equipment and Materials for SPED Inclusive Learning Resource Center (ILRC) | 2000000 |  | COMPETITIVE BIDDING |  |  |  | PROVERBS ENTERPRISES
18 |  |  | TVL | 2160791 |  | COMPETITIVE BIDDING |  |  |  | FAYE AND SAM GENERAL MERCHANDISE | 2, 017,285.00