## pmr 2021 (hidden)
|  | ANNEX A | ANNEX B
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| CY2021 BEFF Repair of Classrooms School | Angeles City National Trade School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 3116479.76 | 0 | 3116479.76 | 3111464.79 | 0 | 3111464.79 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Francisco G. Nepomuceno Memorial High School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2923827.98 | 0 | 2923827.98 | 2916984.81 | 0 | 2916984.81 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Rafael L. Lazatin MHS | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2515459.64 | 0 | 2515459.64 | 2509960.73 | 0 | 2509960.73 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Angeles City National High School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 7096381.72 | 0 | 7096381.72 | 7086139.77 | 0 | 7086139.77 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Cutud ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344133.09 | 0 | 1344133.09 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Northville 15 IS | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Epza Rest ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1800000 | 0 | 1800000 | 1794988.33 | 0 | 1794988.33 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Pulung Bulu ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Sto. Domingo IS | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2700000 | 0 | 2700000 | 2689371.37 | 0 | 2689371.37 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Apung Guidang ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 500000 | 0 | 500000 | 494888.88 | 0 | 494888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Angeles ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 3600000 | 0 | 3600000 | 3593489.6 | 0 | 3593489.6 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Sta. Teresita ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 4950000 | 0 | 4950000 | 4938888.88 | 0 | 4938888.88 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Pampang ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2250000 | 0 | 2250000 | 2245474.37 | 0 | 2245474.37 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Sapalibutad ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344568.33 | 0 | 1344568.33 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Pulung Cacutud ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Salapungan ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1345777.5 | 0 | 1345777.5 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | San Ignacio ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1800000 | 0 | 1800000 | 1794767.82 | 0 | 1794767.82 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Belen Homesite ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344960.94 | 0 | 1344960.94 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Air Force ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344973.74 | 0 | 1344973.74 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
| CY2021 BEFF Repair of Classrooms School | Gueco Balibago ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2250000 | 0 | 2250000 | 2244540.91 | 0 | 2244540.91 |  | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021
GOODS
1 | PRINTING SERVICES FOR THE PROVISION OF EPP, TLE & SENIOR LEARNING RECOURCES FOR QUARTERS 3 & 4 OF SY 2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 17, 2021 | March 24, 2021 | March 26, 2021 | April 12, 2021 | April 12, 2021 | April 12, 2021 | April 14, 2021 | April 15, 2021 | April 29, 2021 | May 3, 2021 | May 17 2021 | May 17 2021 |  | 6149329 |  |  | 4796476.62 |  | 4796476.62 | COA and ACPST-CCI | March 19, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021
2 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR KINDER TO GRADE 3 LEARNERS FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 18, 2021 | March 24, 2021 | March 30, 2021 | April 13, 2021 | April 13, 2021 | April 13, 2021 | April 14, 2021 | April 15, 2021 | April 26, 2021 | May 3, 2021 | May 17 2021 | May 17 2021 |  | 6051427.26 |  |  | 3624788.6 |  | 3624788.6 | COA and ACPST-CCI | March 23, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021
3 | PROCUREMENT OF PRINTERS AND INK FOR THE PROVISION OF LEARNING RESOURCES FOR ARTS, PHYSICAL EDUCATION, ARALING PANLIPUNAN, EDUKASYON PAGPAPAPAKATAO, AND MUSIC FOR QUARTER 3 SY2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 19, 2021 | March 24, 2021 | March 31, 2021 | April 15, 2021 | April 15, 2021 | April 15, 2021 | April 16, 2021 | April 19, 2021 | April 26, 2021 | April 28, 2021 | May 28, 2021 | May 28, 2021 |  | 1947250 |  |  | 1928722 |  | 1928722 | COA and ACPST-CCI | March 23, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021
5 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 -BATCH 2 | DepEd Angeles City |  | Competitive Bidding | April 23, 2021 | April 30, 2021 | May 11, 2021 | May 18, 2021 | May 18, 2021 | May 18, 2021 | May 19, 2021 | May 21, 2021 | May 24, 2021 | May 26, 2021 | June 9, 2021 | June 9, 2021 |  | 2788959.07 |  |  | 2765679 |  | 2765679 | COA and ACPST-CCI | May 4, 2021 | May 11, 2021 | May 11, 2021 | May 11, 2021 | May 11, 2021 | June 2, 2021
7 | PROCUREMENT OF LONG BONDPAPERS FOR THE PROVISION OF LEARNING RESOURCES FOR QUARTER 3 SY2020-2021 - BATCH 2 | DepEd Angeles City |  | Competitive Bidding | N/A | June 23, 2021 | July 1, 2021 | July 13, 2021 | July 13, 2021 | July 13, 2021 | July 14, 2021 | July 16, 2021 | July 26, 2021 | July 27, 2021 | August 14, 2021 | August 14, 2021 |  | 1009060 |  | 6149329 | 1009018 |  | 1009018 | COA and ACPST-CCI | June 16, 2021 | June 16, 2021 | June 16, 2021 | June 16, 2021 | June 16, 2021 | August 7, 2021
8 | PROCUREMENT OF A4 SIZE BOND PAPERS FOR THE IMPLEMENTATION OF BE-LCP PROVISION OF LEARNING RESOURCES AS PER JOINT MEMORANDUM DM-OUCI-2021-107 DATED APRIL 12, 2021 | DepEd Angeles City |  | Competitive Bidding | N/A | June 3, 2021 | June 10, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 9, 2021 | July 12, 2021 | July 27, 2021 | July 27, 2021 |  | 1002765 |  | 6051427.26 | 732, 294.00 |  | 732, 294.00 | COA and ACPST-CCI | June 3, 2021 | June 3, 2021 | June 3, 2021 | June 3, 2021 | June 3, 2021 | July 20, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 |  | 1412287 |  | 1947250 | 1388742 |  | 1388742 | COA and ACPST-CCI | August 11, 2021 | August 24, 2021 | August 24, 2021 | August 24, 2021 | August 24, 2021 | September 28, 2021
10 | Procurement of Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System | DepEd Angeles City |  | Competitive Bidding | August 12, 2021 | August 16, 2021 | August 23, 2021 | September 7, 2021 | September 7, 2021 | September 7, 2021 | September 9, 2021 | September 13, 2021 | September 24, 2021 | September 27, 2021 | November 27, 2021 | November 27, 2021 |  | 1000000 |  | 962907 | 940000 |  | 940000 | COA and ACPST-CCI | August 3, 2021 | August 16, 2021 | August 16, 2021 | August 16, 2021 | August 16, 2021 | November 20, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 |  | 6911464 |  | 2788959.07 | P 4,892,572.00 |  | P 4,892,572.00 | COA and ACPST-CCI | August 2, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | September 28, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 |  | 11133714 |  | 1009060 | 7, 562, 043.00 |  | 7, 562, 043.00 | COA and ACPST-CCI | August 2, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | September 28, 2021
| Procurement of Long Bond Papers for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (18,798 reams) | DepEd Angeles City |  | Competitive Bidding | November 16, 2021 | November 17, 2021 | November. 25, 2021 | November. 29, 2021 | November. 29, 2021 | November 29, 2021 | December 1, 2021 | December 3, 2021 | December 10, 2021 | December 13, 2021 | December 28, 2021 | December 28, 2021 |  | 3571671 |  | 1002765 | 2488859.2 |  | 2488859.2 | COA and ACPST-CCI | November 18, 2021 | November 18, 2021 | November 18, 2021 | November 18, 2021 | November 18, 2021 | December 21, 2021
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (8075 pcs) | DepEd Angeles City |  | Competitive Bidding | September 14, 2021 | September 20, 2021 | September 28, 2021 | November 16, 2021 | November 16, 2021 | November 16, 2021 | November 17, 2021 | November 17, 2021 | November 19, 2021 | November 23, 2021 | December 15, 2021 | December 15, 2021 |  | 2018892 |  | 1412287 | P 1, 287,962.50 |  | P 1, 287,962.50 | COA and ACPST-CCI | September 21, 2021 | November 10, 2021 | November 10, 2021 | November 10, 2021 | November 10, 2021 | December7, 2021
| School Based Feeding Program | DepEd Angeles City |  | (2 Failed Bidding) Negotiated Bidding | October 26, 2021 | November 4, 2021 | November 9, 2021 | November 12, 2021 | November 12, 2021 | November 12, 2021 | November 15, 2021 | November 18, 2021 | November 22, 2021 | November 25, 2021 | January 31, 2021 | January 31, 2021 |  | 12, 875,760.00 |  | 1000000 | 12869751.31 |  | 12869751.31 | COA and ACPST-CCI | October 28, 2021 | October 28, 2021 | October 28, 2021 | October 28, 2021 | October 28, 2021
| Purchase of SPED Equipment and Materials for SPED Inclusive Learning Resource Center (ILRC) | DepEd Angeles City |  | Competitive Bidding | October 20, 2021 | October 25, 2021 | November 3, 2021 | November 16, 2021 | November 16, 2021 | November 16, 2021 | November 17, 2021 | November 19, 2021 | November 22, 2021 | November 23, 2021 | December 23, 2021 | December 23, 2021 |  | 2000000 |  | 6911464 | 1795000 |  | 1795000 | COA and ACPST-CCI | October 28, 2021 | November 9, 2021 | November 9, 2021 | November 9, 2021 | December 15, 2021
| Procurement of Technical-Vocational-Livelihood (TVL) Learning Tools and Equipment | DepEd Angeles City |  | Competitive Bidding | November 22, 2021 | November 24, 2021 | December 2, 2021 | December 14, 2021 | December 14, 2021 | December 14, 2021 | December 15, 2021 | December 17, 2021 | January 3, 2022 | January 10, 2022 | February 15, 2022 | February 15, 2022 |  | 2160791 |  | 11133714 | 2,017, 285.00 |  | 2,017, 285.00 | COA and ACPST-CCI | November 26 2021 | December 7, 2021 | December 7, 2021 | December 7, 2021 | December 7, 2021
12, 875,760.00
2000000
2160791
|  |  |  | Prepared: | [10 empty] | Reviewed: | [5 empty] | 0
|  |  | Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  |  | MARIA CRISTINA S. SARMIENTO | MARIA CRISTINA S, SARMIENTO | [7 empty] | FERNANDINA P. OTCHENGCO, PhD CESE |  |  | FERNANDINA P. OTCHENGCO | [7 empty] | MA. IRELYN P. TAMAYO, PhD CESE
|  |  | BAC Secretariat | BAC Secretariat | [7 empty] | BAC Chairperson |  |  | BAC Chair | [7 empty] | Head of the Procuring Entity

## PMR 2022
CY 2022 SDO ANGELES CITY PROCUREMENT MONITORING REPORT
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | CY2022 BEFF Repair of Classroom School Building at Lourdes North West Elementary School | SDO Angeles City | LNWES | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 2750000 | 2739845.02 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
2 | CY2022 BEFF Repair of Classroom School Building at Virgen Delos Remedios Elementary School | SDO Angeles City | VDRES | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 2100000 | 2088366.63 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
3 | CY2022 BEFF Repair of Classroom School Building at Dr. Clemente N. Dayrit Sr. Elementary School | SDO Angeles City | CLEMENDES | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 1500000 | 1490072.29 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
4 | CY2022 BEFF Repair of Classroom School Building at DON AMBROCIO MENDIOLA INTEGRATED School | SDO Angeles City | DAMIS | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 1650000 | 1640121 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
[20 empty] | 8000000 | 7958404.94 |  |  | 41595.06
GOODS
1 | Printing Services for the Development and Production of Self Learning Modules for Quarter 3 SY 2021-2022 Lot 1 | SDO Angeles City | All public Schools | Competitive Bidding | Dec 9, 2021 | Dec 14, 2021 | Dec 22, 2021 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 5, 2022 | Feb 9, 2022 | Feb. 14, 2022 | Feb. 15, 2022 | 45 days | March 31, 2022 | GAA |  |  | 9902000 | 8888035.2 |  |  | COA and ACPST-CCI | Dec 14, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 |  | Completed
2 | Printing Services for the Development and Production of Self Learning Modules for Quarter 4 SY 2021-2022 Lot 2 | SDO Angeles City | All public Schools | Competitive Bidding | Dec 9, 2021 | Dec 14, 2021 | Dec 22, 2021 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 5, 2022 | Feb 9, 2022 | Feb. 14, 2022 | Feb. 15, 2022 | 45 days | March 31, 2022 | GAA |  |  | 6313000 | 5679174.8 |  |  | COA and ACPST-CCI | Dec 14, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 |  | Completed
3 | Procurement of USB -OTG from Savings of the Development and Production of Self Learning Modules | SDO Angeles City | All public Schools | Competitive Bidding | Jan 27, 2022 | Feb 8-22, 2022 | Feb. 15, 2022 | Feb 22, 2022 | Feb 22, 2022 | Feb 22, 2022 | Feb 23, 2022 | Apr 29, 2022 | May 2, 2022 | May 11, 2022 | 30 days | June 9, 2022 | GAA |  |  | 1647790 | 1345249.6 |  |  | COA and ACPST-CCI | Feb 8, 2022 | Feb 15, 2022 | Feb 15, 2022 | Feb 15, 2022 | Feb 15, 2022 |  | Completed
5 | School-Based Feeding Program | SDO Angeles City | All public Schools | Competitive Bidding | Mar 25, 2022 | Apr 4-19, 2022 | Apr 12, 2022 | Apr 25, 2022 | Apr 25, 2022 | Apr 25, 2022 | Apr 28, 2022 | Apr 29, 2022 | May 2, 2022 | May 13. 2022 | 30 days | June 11, 2022 | GAA |  |  | 6437880 | 5674872 |  |  | COA and ACPST-CCI | Apr 4, 2022 | Apr 18, 2022 | Apr 18, 2022 | Apr 18, 2022 | Apr 18, 2022 |  | Completed
7 | Procurement of Bluetooth Speakers from CY2022 Savings | SDO Angeles City | All public Schools | Competitive Bidding | May 19, 2022 | June 23-30, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | July 25, 2022 | July 27, 2022 | Aug 8, 2022 | 45 days | September 21, 2022 | GAA |  |  | 14245829.2 | 9768384 |  |  | COA and ACPST-CCI | June 23, 2022 | July 7, 2022 | July 7, 2022 | July 7, 2022 | July 7, 2022 |  | Completed
8 | Procurement of DEpEd Computerization Program | SDO Angeles City | All public Schools | Competitive Bidding | July 25, 2022 | August 1-17, 2022 | August 5, 2022 | August 18, 2022 | August 18, 2022 | August 18, 2022 | August 22, 2022 | August 30, 2022 | August 31, 2022 | September 21, 2022 | 30 days | October 13, 2022 | GAA |  |  | 1000000 | 998000 |  |  | COA and ACPST-CCI | [6 empty] | Completed
9 | Procurement of Printer's Inks from 2022 Savings | SDO Angeles City | All public Schools | Competitive Bidding | August 15, 2022 | August 17-23, 2022 | August 23, 2022 | September 5, 2022 | September 5, 2022 | September 5, 2022 | September 6, 2022 | September 13, 2022 | September 14, 2022 | September 21, 2022 | 30 days | October 4, 2022 | GAA |  |  | 2346600 | 1583010 |  |  | COA and ACPST-CCI | [6 empty] | Completed
10 | Procurement of Bondpapers from 2022 Savings | SDO Angeles City | All public Schools | Competitive Bidding | September 14, 2022 | September 14-21,2022 | September 21, 2022 | October 5, 2022 | October 5, 2022 | October 5, 2022 | October 6, 2022 | October 11, 2022 | October 12, 2022 | October 18, 2022 | 30 days | November 24, 2022 | GAA |  |  | 2100845.2 | 2100830 |  |  | COA and ACPST-CCI | [6 empty] | Completed
11 | CY2022 CONVERSION OF SPED CENTER TO INCLUSIVE LEARNING RESOURCE CENTER (ILRC) | SDO Angeles City | Angeles ES | Competitive Bidding | October 21, 2022 | October 25, 2022 | November 2, 2022 | November 14, 2022 | November 14, 2022 | November 14, 2022 | November 15, 2022 | November 22, 2022 | November 23, 2022 | December 5, 2022 | 90 days |  | GAA |  |  | 3600000 | 3589571.21 |  |  | COA and ACPST-CCI | [6 empty] | On Going
[20 empty] | 47593944.4 | 39627126.81
[20 empty] | 7966817.59 | 0
Prepared by: |  |  |  | Recommended for Approval by: | [7 empty] | Approved: | [10 empty] | APPROVED: |  |  | Approved:
MARIA CRISTINA S. SARMIENTO |  |  |  | FERNANDINA P. OTCHENGCO, PhD CESE | [7 empty] | MA. IRELYN P. TAMAYO PhD, CESO V | [10 empty] | MA. IRELYN P. TAMAYO, PhD CESE |  |  | MA. IRELYN P. TAMAYO PhD, CESO V
BAC Secretariat |  |  |  | BAC Chairperson | [7 empty] | Head of Procuring Entity | [10 empty] | Head of the Procuring Entity |  |  | Head of Procuring Entity

## Sheet1 (hidden)
FY 2022 EARLY PROCUREMENT ACTIVITIES SCHEDULE – 2nd Batch
EPA for the Development and Production of Self- Learning Modules FY2022-2023
ABC -
PRE-PROCUREMENT FOR THE SAVINGS FROM EARLY PROCUREMENT AND THE QUARTER 4 PROVISION OF LEARNING RESOURCES FOR SY 2021-2022 UNDER BE-LCP AS PER JM DM-CI-2022-029 DATED JANUARY 28, 2022 (ABC - P 3,923,111.00)
PROCUREMENT SCHEDULE FOR 2022 SAVINGS
P 14,245,829.20
PROCUREMENT SCHEDULE FOR BLUETOOTH SPEAKERS FROM 2022 SAVINGS
P 14,245,829.20
PROPOSED PROCUREMENT SCHEDULE FOR CY 2022 BEFF REPAIR OF SCHOOL BUILDING
P 8,000,000.00
(CLEMENDES, LNWES, DAMIS AND VDRES)
PROPOSED PROCUREMENT SCHEDULE FOR DEPED COMPUTERIZATION PROGRAM
P 1,000,000.00
Repeat Order Method for the Procurement of Technical-Vocational-Livelihood (TVL) Learning Tools and Equipment amounting to One Hundred Forty-Three Thousand Five Hundred Six Pesos (P 143,506.00
PROCUREMENT SCHEDULE FOR BONDPAPERS AND PRINTER’S INKS FROM SAVINGS
PROCUREMENT SCHEDULE FOR BONDPAPERS FROM SAVINGS (2ND Posting)
PROCUREMENT SCHEDULE FOR CONVERSION OF SPED CENTER TO INCLUSIVE LEARNING RESOURCE CENTER (ILRC) P 3,600.000.00