|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Stage** | **Activity** | **Deadline** | **Duration** | **Deadline** |
| 0 | Pre-Procurement Meeting |  | 1 cd | October 28, 2020  10:00 A.M. |
| 1 | Preparation of Bidding Documents |  |  | October 29, 2020 |
| 2 | Advertisement/Posting of Invitation to Bid |  |  | November 6, 2020 |
| 3 | Issuance and Availability of Bidding Documents |  | 7cd | November 9, 2020  to November 23, 2020 |
| 4 | Pre-Bid Conference | At least 12 cd before Stage 7 | 1 cd | November 11, 2020  10:00 A.M |
| 5 | Request for Clarification | At least 10 cd before Stage 7 | 1 cd | November13, 2020 |
| 6 | Supplemental/Bid Bulletins | 7 cd before Stage 7 | 1 cd | November 16, 2020 |
| 7 | Submission and Receipt of Bids |  | 1 cd | November 23, 2020  8:00-8:30 A.M. |
| 8 | Opening of Bids and Eligibility Check Bid Evaluation |  | 1 cd | November 23, 2020  10:00 A.M., Via Google Meet |
| 9 | Post Qualification |  | 1 cd | November 24, 2020 |
| 10 | Preparation and Approval of Resolution to Award |  | 1 cd | November 25, 2020 |
| 11 | Issuance of Notice of Award |  | 1 cd |  |
| 12 | Contract Preparation and signing |  | 1 cd |  |
| 13 | Perfection and Approval of Contract |  | 1 cd |  |
| 14 | Issuance of NTP |  | 1 cd |  |

**Batch 2- Basic Education Learning Continuity Plan - Provision of Learning Resources**

**ABC – P 5,508,000.00**

Reviewed:

**LYN V. LANSANGAN EdD**

BAC -Vice Chairman

Approved:

**FERNANDINA P. OTCHENGCO PhD, CESE**

BAC Chair